## Sheet1
# | product Items | story points | risk level | importance | release group
1 | as a user I should be able to create a uniquely Identifiable profile | 3 | high | 1 | 1
2 | as a user I should be able to login to my profile | 3 | high | 1 | 1
3 | As a doer, I want to add a habit, giving it a brief title, reason, and date to start. | 3 | medium | 1 | 1
4 | As a doer, I want a habit to have a plan for what days of the week it should regularly occur. | 3 | high | 1 | 1
14 | As a doer, I want to denote a habit event when I have done a habit as planned. | 2 | medium | 1 | 1
18 | As a doer, I want to edit the details of a habit event of mine. | 2 | medium | 1 | 1
19 | As a doer, I want to delete a habit event of mine. | 2 | medium | 1 | 1
5 | As a doer, I want to view a given habit and its details. | 3 | low | 2 | 1
6 | As a doer, I want to edit the details of a habit of mine. | 2 | medium | 2 | 1
7 | As a doer, I want to delete the details of a habit of mine. | 2 | medium | 2 | 2
12 | As a doer, I want to see a list of all my habits. | 3 | high | 2 | 2
9 | As a doer, I want to see what habits I need to do today. | 3 | medium | 2 | 2
13 | As a doer, I want for each habit on the list, a visual indicator to show how closely I am following its plan over time. | 1 | low | 2 | 2
17 | As a doer, I want to view a given habit event and all its available details. | 2 | low | 2 | 2
20 | As a doer, I want to ask another doer to follow all their habits. | 2 | medium | 2 | 2
21 | As a doer, I want to grant or deny another doer permission to follow all my habits. | 2 | high | 2 | 2
22 | As a doer, I want to view the habits and visual indicators of the other doers I am granted to follow. | 1 | medium | 2 | 2
8 | As a doer, I want a habit title to be up to 20 characters and habit reason to be up to 30 characters. | 3 | low | 3 | 2
15 | As a doer, I want a habit event to have an optional description of up to 20 characters. | 1 | low | 3 | 2
16 | As a doer, I want a habit event to have an optional photograph to record what happened. | 1 | low | 3 | 2
23
24
25
26
27
28
29
30
31
32